## Sheet1
Product Backlog
Priority | Description | Name
Create preliminary prototype with working buttons
Create preliminary script with distinct options and some content regardless of path chosen
1 | Second prototype: braille buttons, replay button, volume control | Prototype 2
1 | Create second script | Script 2
1 | Create processing program to read the script for demonstrating prototpye 2 | Program
2 | Record audio files for the script | Rec
3 | Modify program to read audio files of script 2 | Program 2
4 | Create final thing
Backlog Item | subtasks | Who | Time expected (hours) | Total | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22
Prototype 2 | Research braille and button options | Julia, Szymon, Ny | 0.5 | 1.2 | 2019-11-08: 1; 2019-11-14: 0.2
| make skeleton (+ replay button?) | Szymon | 0.2 | 0.2 | 2019-11-11: 0.2
| add braille to buttons | Szymon | 0.2 | 0.1 | 2019-11-11: 0.1
| add volume control |  | 0.2 | 0
Script 2 | Finish writing enough for prototype 2 | Julia, Ny | 4 | 4.5 | 2019-11-11: 0.7; 2019-11-12: 0.3; 2019-11-14: 1.5; 2019-11-17: 2
| Finish writing entire script | Julia, Ny | 6 | 0
| Edit script to ensure continuity, consistent game time, and acceptable logic |  | 2 | 0
Program | Create processing classes to handle multi-choice story structure | Eddy | 1 | 1 | 2019-11-14: 0.5; 2019-11-17: 0.5
| Create program that can run the script, only displaying text | Eddy | 2 | 2 | 2019-11-14: 0.5; 2019-11-17: 1.5
| Feed script 2 into the program for presenting prototype 2 |  | 1 | 0
Total: |  |  | 16.6 | 7.8 |  |  |  | 1 | 0.3 | 0 | 2.5 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Rec | Record audio files of script | Julia, Ny | 3 | 0
| Review audio files to ensure quality and that they are compatible with processing/arduino |  | 1 | 0
Program 2 | Modify program to take in and read audio (.wav) files | Eddy | 3 | 0 | 2019-11-14: 2
| Feed audio files into program for final presentation |  | 3 | 0
|  | Date | Actual (hours) | Ideal (hours)
|  | 2019-11-04 | 20 | 20
|  | 2019-11-11 | 17 | 15
|  | 2019-11-18 | 12 | 10
|  | 2019-11-25 |  | 5
|  | 2019-12-03 |  | 0